## Dashboard
Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness.
Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness. | Dashboard for implementation status, roadmap health, and QA readiness.
Metric | Value |  | Status | Count | Notes
Implemented items | 18 |  | Implemented | 18 | Live or built in code
Planned/future items | 12 |  | In Progress | 0 | Currently being built
P0 open items | 1 |  | Planned | 11 | Should be built for next pilots
Next phase items | 7 |  | Future | 1 | Later phase / integrations
Total tracked items | 30 |  | Blocked | 0 | Needs decision or dependency
|  |  | Deferred | 0 | Not needed for MVP

## Functionality Tracker
ID | Area | Functionality | Status | Current Implementation | Files / Source | Owner | Priority | Release | Next Step
AG-001 | Public Marketing | Agency partner landing page | Implemented | Public agency partner page at /partners/agency with 14-day pilot positioning and no-integration copy. | src/pages/partners/AgencyPartnerPage.tsx | Product | P0 | Pilot MVP | Use in outreach
AG-002 | Application | Agency partner application type | Implemented | Partner application flow supports type=agency without removing academic, business, student flows. | src/pages/partners/PartnerApplicationPage.tsx; src/types.ts | Product | P0 | Pilot MVP | Monitor incoming applications
AG-003 | Roles/Auth | agency_partner role | Implemented | Approved agency users can be assigned agency_partner role and access agency dashboard. | functions/src/triggers.ts; src/pages/AgencyPartnerDashboard.tsx | Engineering | P0 | Pilot MVP | Verify on next real approval
AG-004 | Data | Agency branch profile | Implemented | agencyBranches collection stores branch owner, slug, contact, status, invite limit, color. | src/types.ts; functions/src/triggers.ts | Engineering | P0 | Pilot MVP | Add logo support later
AG-005 | Admin | Admin agency dashboard links | Implemented | Admin Partners tab lists approved branches with dashboard and invite actions. | src/pages/admin/components/PartnerApplicationManagement.tsx | Engineering | P0 | Pilot MVP | Use for demos
AG-006 | Agency Dashboard | Dashboard shell | Implemented | Agency partner dashboard reuses partner dashboard conventions with agency-first tabs. | src/pages/AgencyPartnerDashboard.tsx | Engineering | P0 | Pilot MVP | Improve empty states as pilots grow
AG-007 | Agency Dashboard | Prep Pipeline tab | Implemented | Groups candidate prep sessions by started, resume imported, reviewed, ready, shared. | src/pages/AgencyPartnerDashboard.tsx | Product | P0 | Pilot MVP | Add search/filter
AG-008 | Agency Dashboard | Invite Link tab | Implemented | Branch invite link and recruiter script are visible to the agency. | src/pages/AgencyPartnerDashboard.tsx | Product | P0 | Pilot MVP | Add QR/download assets
AG-009 | Agency Dashboard | Ready Reports tab | Implemented | Shared sessions show readiness summary and resume link after consent. | src/pages/AgencyPartnerDashboard.tsx | Product | P0 | Pilot MVP | Add report PDF/export
AG-010 | Agency Dashboard | Pilot Metrics tab | Implemented | Shows candidates started, shared reports, average score lift. | src/pages/AgencyPartnerDashboard.tsx | Product | P0 | Pilot MVP | Add time saved metric
AG-011 | Candidate Prep | Agency prep portal | Implemented | Candidate opens /prepare/{slug}, signs in, selects/creates resume, and shares readiness when ready. | src/pages/AgencyPreparePage.tsx | Engineering | P0 | Pilot MVP | Test with real branch user
AG-012 | Candidate Prep | Prep session upsert | Implemented | Creates/updates agencyPrepSessions from candidate activity and current resume score. | src/services/agencyPartnerService.ts | Engineering | P0 | Pilot MVP | Add invited state later
AG-013 | Consent | Candidate readiness sharing | Implemented | Candidate consent updates status=shared, report summary, score delta, sharedAt, resumeSharePath. | src/services/agencyPartnerService.ts | Engineering | P0 | Pilot MVP | Add revoke history
AG-014 | Resume Sharing | Viewer-only resume link | Implemented | Agency readiness flow turns on public viewer link without editor permission. | src/services/agencyPartnerService.ts | Engineering | P0 | Pilot MVP | Confirm permission copy
AG-015 | Security | Firestore rules for agency data | Implemented | Agency partners can read only branch sessions; candidate owns session updates; admin can read all. | firestore.rules | Engineering | P0 | Pilot MVP | Deploy rules if changed
AG-016 | Resume Sharing | Ready for recruiter review toggle | Implemented | Share modal includes readiness signal after public access is enabled. | src/components/ShareResumeModal.tsx | Product | P1 | Pilot MVP | Collect recruiter feedback
AG-017 | Public Resume | Recruiter readiness banner | Implemented | Public resume shows readiness banner when candidate marks resume recruiter-ready. | src/pages/PublicResumePage.tsx | Product | P1 | Pilot MVP | Refine wording with pilot feedback
AG-018 | Demo | Demo branch and sessions | Implemented | Demo Champaign agency branch and sample sessions/resumes exist in production Firestore. | Firestore production data | Founder | P0 | Pilot Demo | Refresh before meetings
AG-019 | Limits | Pilot seat enforcement | Planned | Enforce inviteLimit and show remaining seats to agency/admin. | New service/rules work | Engineering | P1 | Next | Define seat behavior
AG-020 | Export | Agency CSV export | Planned | Export shared candidates and readiness summaries for agency operations. | New dashboard action | Engineering | P1 | Next | Define fields
AG-021 | Notifications | Candidate invite email | Planned | Agency/admin can send candidate prep invites with branch link. | Email/Novu/Firebase mail | Engineering | P1 | Next | Draft template
AG-022 | Branding | Branch logo/color editor | Planned | Admin or agency owner can edit logo, color, and branch display copy. | Agency branch settings | Product | P2 | Next | Design simple settings panel
AG-023 | Consent | Consent revoke and audit history | Planned | Candidate can revoke agency sharing and system tracks consent timestamps. | Rules/service/UI | Engineering | P1 | Next | Model audit events
AG-024 | Recruiter Workflow | Recruiter notes and tags | Planned | Agency can add private branch notes/tags to shared candidates. | New collection or session fields | Product | P2 | Later | Validate need
AG-025 | Billing | Pilot pricing and subscription flow | Planned | Convert successful pilot to monthly branch plan. | Stripe/Billing | Founder | P2 | Later | Choose pricing after pilots
AG-026 | Integrations | Webhook or ATS API sync | Future | Push finalized resume data into ATS only after pilot proves value. | Cloud Functions/API | Engineering | P3 | Future | Do not lead with this
AG-027 | Outcomes | Placement outcome tracking | Planned | Track placed, not placed, interview scheduled, client sent outcomes. | Agency dashboard | Product | P2 | Later | Define statuses
AG-028 | Reporting | Branch ROI report | Planned | Summarize score lift, time saved, shared reports, placements, conversion rate. | Dashboard/report export | Product | P1 | Next | Create after first pilot
AG-029 | Search | Agency candidate search/filter | Planned | Search sessions by name/email/status/score/readiness. | Agency dashboard | Engineering | P1 | Next | Add once session list grows
AG-030 | Legal | Agency pilot terms and privacy copy | Planned | Simple terms/privacy language for agency branch pilots and candidate sharing. | Docs/public copy | Founder | P0 | Before Paid | Draft before paid pilot

## Roadmap
Phase | Theme | Feature / Workstream | Owner | Status | Dependency | Priority | Target
Now | Demo readiness | Use demo branch and current MVP in live agency conversations. | Founder | Ready | Demo branch | High | This week
Now | Agency outreach tracking | Keep branch conversations, contacts, follow-ups, and deal status in the agency pipeline workbook. | Founder | Ready | Pipeline workbook | High | This week
Next | Seat limits | Enforce invite limit and show used/remaining pilot seats. | Engineering | Planned | agencyPrepSessions count | High | Before paid pilot
Next | CSV export | Let agency export shared readiness reports for branch operations. | Engineering | Planned | Ready Reports tab | High | Before paid pilot
Next | Consent revoke | Candidate can revoke shared access and agency report updates accordingly. | Engineering | Planned | shareConfig + session audit | High | Before paid pilot
Next | Pilot ROI report | Generate branch summary of score lift, shared candidates, time saved, and placement outcomes. | Product | Planned | Pilot metrics | High | After first pilot
Later | Recruiter notes/tags | Agency can tag and note shared candidate records. | Product | Planned | Agency dashboard | Medium | After usage proof
Later | ATS/webhook integration | Optional ATS sync for finalized profiles once a branch pays. | Engineering | Future | API design | Low | Paid phase
Later | Billing conversion | Stripe plan for branch license or volume tier. | Founder | Future | Pricing decision | Medium | After first pilot

## QA Checklist
ID | Test Area | Role | Test Step | Status | Notes
QA-001 | /partners/agency loads publicly | Public visitor | Open route and confirm CTA routes to /partners/apply?type=agency | Passed | Hosting deployed 2026-05-30
QA-002 | Agency application type appears in admin | Admin | Submit type=agency and confirm row/type display | Needs Real Pilot Test | Use next agency application
QA-003 | Approved agency gets agency_partner role | Admin/Function | Approve agency application and inspect user role | Needs Real Pilot Test | Requires function deploy/trigger
QA-004 | Branch invite link resolves | Candidate | Open /prepare/{slug} and confirm branch loads | Passed | Demo branch available
QA-005 | Prep session creates/updates | Candidate | Sign in, open prep link, select resume, confirm session | Passed Demo | Demo session seeded
QA-006 | Agency progress-only view before consent | Agency/Admin | Confirm dashboard shows status/score but not full resume until shared | Passed Demo | Review privacy with real branch
QA-007 | Candidate share readiness | Candidate | Click Share readiness report and confirm session status shared | Passed Demo | Monitor first real user
QA-008 | Agency opens shared report/resume after consent | Agency/Admin | Open Ready Reports and resume link | Passed Demo | Viewer-only mode
QA-009 | Share modal readiness toggle | Candidate | Toggle Ready for recruiter review and confirm public banner | Passed Build | Frontend deployed
QA-010 | Existing business partner flow unchanged | Regression | Verify business dashboard and partner application still load | Not Run | Run before broader release

## Data Lists
Statuses | Priorities | Roadmap Priority | QA Status
Implemented | P0 | High | Passed
In Progress | P1 | Medium | Passed Demo
Planned | P2 | Low | Passed Build
Future | P3 |  | Needs Real Pilot Test
Blocked |  |  | Not Run
Deferred |  |  | Blocked